## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 144
|  | Days In Sprint: |  |  |  | 6
Burndown Chart
User Stories |  | Days (Points Completed) | [5 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | Task Balance | Percentage Completed
Create post for news and breaking news | 36 | 5 | 7 | 7 | 6 | 3 | 4 | 4 | 88.89%
Create schedule for different programs or events. | 36 | 3 | 7 | 11 | 6 | 4 | 5 | 0 | 100%
Live streaming news system | 18 | 6 | 6 | 5 | 0 | 0 | 0 | 1 | 94.44%
Weather forecast updates system | 18 | 0 | 0 | 0 | 7 | 6 | 4 | 1 | 94.44%
Contact and enquiry system | 24 | 2 | 11 | 11 | 0 | 0 | 0 | 0 | 100%
Option to view and read the company details | 12 | 0 | 0 | 0 | 6 | 3 | 3 | 0 | 100%
Effort Remaining | 144 | 128 | 97 | 63 | 38 | 22 | 6 | 6 | 95.83%
Ideal Trend | 144 | 120 | 96 | 72 | 48 | 24 | 0
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days